## Features
Module | Feature | Criteria | Estimate | Risk | Total Time | Priority | Notes
Admin Portal | Admin Login &Logout | Admin authentication. | XS (2) | No Risk (1) | 2 | Must
Admin Portal | Cancellation Review | Review ride cancellations. | XS (2) | No Risk (1) | 2 | Must
Admin Portal | Driver Administrative Approval (Activation Gate) | Approve/reject driver onboarding and activate account; enforce gate so driver cannot go online before approval. | S (5) | No Risk (1) | 5 | Must
Admin Portal | Driver Document Review | Admin reviews submitted driver documents, views images/PDFs, marks valid/invalid, requests resubmission with reason. | S (5) | Low (1.1) | 5.5 | Must
Admin Portal | Manage Drivers | Approve/reject drivers. | XS (2) | No Risk (1) | 2 | Must
Admin Portal | Manage Riders | View/suspend/block riders. | XS (2) | No Risk (1) | 2 | Must
Admin Portal | Operational Reports | Basic operational reports (non-BI). | M (10) | No Risk (1) | 10 | Must
Admin Portal | Pricing Configuration | Configure pricing rules. | S (5) | Low (1.1) | 5.5 | Must
Admin Portal | View Active Rides | Monitor active rides. | M (10) | Medium (1.25) | 12.5 | Must
Admin Portal | View Completed Rides | Search completed rides. | S (5) | No Risk (1) | 5 | Must
Admin Portal | Safety- Incident History | View incident logs. | S (5) | No Risk (1) | 5 | Must
Admin Portal | Safety- SOS Case Management | Track and resolve SOS incidents. | S (5) | No Risk (1) | 5 | Must
Driver | Accept / Reject Ride | Accept or decline assigned ride. | S (5) | Medium (1.25) | 6.25 | Must
Driver | Administrative Approval Before Activation | Admin approval gate before driver can go online and accept rides. | XS (2) | No Risk (1) | 2 | Must
Driver | Availability Management (Online/Offline) | Driver availability toggle and enforcement in dispatch logic. | XS (2) | No Risk (1) | 2 | Must
Driver | Complete Trip | Mark trip as completed. | XS (2) | No Risk (1) | 2 | Must
Driver | Driver Document Review Workflow | Backend workflow to support admin review and status updates of driver documents. | XS (2) | Medium (1.25) | 2.5 | Must
Driver | Driver Document Submission | Upload required driver documents during onboarding. | XS (2) | No Risk (1) | 2 | Must
Driver | Driver Trip History & Earnings Summary | View completed trips and basic earnings breakdown. | S (5) | Low (1.1) | 5.5 | Must
Driver | Earnings View | View earnings per trip. | XS (2) | No Risk (1) | 2 | Must
Driver | Go Online / Offline | Set availability status. | XS (2) | No Risk (1) | 2 | Must
Driver | Receive Ride Request | Receive incoming ride notifications. | XS (2) | Medium (1.25) | 2.5 | Must
Driver | Start Trip | Start trip after pickup. | XS (2) | Low (1.1) | 2.2 | Must
Driver | Safety - SOS Button (Driver) | Driver-triggered SOS. | XS (2) | No Risk (1) | 2 | Must
Identity & Compliance | Child Ride Flag | Capture and enforce child (<12) indicator. | S (5) | Low (1.1) | 5.5 | Must | Identity Verification Provider? Date of Birth ? OCR for front ? Admin approval gate
Identity & Compliance | Driver ID Verification | National ID + selfie + document upload for drivers. | S (5) | Medium (1.25) | 6.25 | Must
Identity & Compliance | Rider ID Verification | National ID + selfie + age validation for riders. | XS (2) | Low (1.1) | 2.2 | Must
Identity & Compliance | Verification Status Tracking | Pending/Approved/Rejected flows. | XS (2) | Medium (1.25) | 2.5 | Must
Identity & Compliance | Women-only Enforcement | Prevent non-eligible users from rides. | S (5) | Low (1.1) | 5.5 | Must | Identity Verification Provider? Date of Birth ? OCR for front ? Admin approval gate
Notifications | Notification Logs | Store and view sent notifications. | S (5) | No Risk (1) | 5 | Must
Notifications | Push Notifications | Push notifications for ride events. | XS (2) | Low (1.1) | 2.2 | Must
Notifications | SMS Notifications | SMS for OTP and safety alerts. | XS (2) | Medium (1.25) | 2.5 | Must
Operational / Platform | Centralized Logging & Tracing | Application-level logs, correlation IDs, request tracing across services. | M (10) | No Risk (1) | 10 | Must
Operations / NFR | Health Checks & Readiness Probes | Implement service health endpoints, dependency checks (DB/PSP/SMS/Maps), and readiness indicators for deployment. | S (5) | Medium (1.25) | 6.25 | Must
Payments | Cancellation Fee Calculation | Apply cancellation fees. | XS (2) | Medium (1.25) | 2.5 | Must
Payments | Initiate Payment | Trigger payment after trip completion. | S (5) | Medium (1.25) | 6.25 | Must
Payments | Payment Failure Handling | Handle failed payments and retry logic. | XS (2) | Medium (1.25) | 2.5 | Must
Payments | Payment Success Handling | Handle successful payments. | XS (2) | Medium (1.25) | 2.5 | Must
Payments | View Payment History | Admin/user view of payments. | S (5) | No Risk (1) | 5 | Must
Platform / Shared | Audit Logging | Audit logs for critical actions. | S (5) | No Risk (1) | 5 | Must
Platform / Shared | Edit User Profile | Edit basic profile info (name, preferences). | XS (2) | No Risk (1) | 2 | Must
Platform / Shared | Localization Framework | Arabic/English UI support and switching. | S (5) | Low (1.1) | 5.5 | Must
Platform / Shared | OTP Resend & Expiry Handling | Handle OTP expiration, resend limits, and retries. | XS (2) | Low (1.1) | 2.2 | Must
Platform / Shared | User Login | Authenticate user using OTP; session creation. | XS (2) | No Risk (1) | 2 | Must
Platform / Shared | User Logout | Terminate user session securely. | XS (2) | No Risk (1) | 2 | Must
Platform / Shared | User Registration (OTP) | Register user using mobile number with OTP validation. | XS (2) | Low (1.1) | 2.2 | Must
Platform / Shared | View User Profile | View personal profile details. | XS (2) | No Risk (1) | 2 | Must
Rider | Cancel Ride | Cancel ride with reason selection. | S (5) | No Risk (1) | 5 | Must
Rider | Rate Trip | Submit rating and feedback. | XS (2) | Low (1.1) | 2.2 | Must
Rider | Real-time Trip Status & Tracking | Live ride status updates and real-time trip tracking for rider during active trip. | M (10) | High (1.5) | 15 | Must
Rider | Request Ride | Create ride request with pickup/destination. | M (10) | High (1.5) | 15 | Must
Rider | Ride Status Updates | Real-time ride status updates across lifecycle (assigned/arrived/started/completed/cancelled) including UI state handling. | S (5) | Medium (1.25) | 6.25 | Must
Rider | Track Driver Location | Real-time driver tracking. | S (5) | High (1.5) | 7.5 | Must
Rider | Trip Completion Screen | Show trip summary after completion. | S (5) | No Risk (1) | 5 | Must
Rider | Trip History | View list of past trips. | XS (2) | Low (1.1) | 2.2 | Must
Rider | View Fare Estimate | Display estimated fare and ETA. | XS (2) | Medium (1.25) | 2.5 | Must
Rider/Driver | In-app Text Communication (Chat) | In-app text messaging between rider and assigned driver during active ride only; block PII sharing; message history for ride duration. | M (10) | High (1.5) | 15 | Must
Rider | Safety-SOS Button (Rider) | Trigger SOS during trip. | XS (2) | No Risk (1) | 2 | Must
Integrations | Payment Provider Integration (PSP) | Integrate external payment provider: initiate payment, handle callbacks/webhooks, status mapping, sandbox/prod config, error handling. | M (10) | High (1.5) | 15 | Must
Integrations | Notification Provider Integration (SMS, Email, Push) | Integrate notification distributors for SMS, Email, and Push; template mapping, retries, failure handling, environment separation. | S (5) | Low (1.1) | 5.5 | Must
Integrations | Maps & Geolocation Integration (Google Maps) | Integrate Google Maps for geocoding, routing, distance & ETA calculation, live tracking, quotas, and API key management. | S (5) | Low (1.1) | 5.5 | Must
Integrations | Google as SSO | Integrate with Google SSO | S (5) | Low (1.1)

## Estimate Summary
Team Efforts
Development Effort | 287.65 | Days
Number of Dev members | 5 | Developers
Release planning | 0.5 | #
Sprint Zero | 1 | #
Stabilization Sprints | 1 | #
Fixing Security Risks | 0.5 | #
Deployment | 0.5 | #
Expected sprints | 9.253 | Sprints | 10 working days per sprint
Project Resources
Role | Count | Duration (days) | Notes
Fullstack Team Lead | 1 | 95
Fullstack Senior Developer | 3 | 95
Fullstack Junior Developer | 1 | 95
Senior QC engineer | 1 | 95
UIUX designer | 1 | 35
UI developer | 0 | 0
Product Owner | 1 | 95
Scrum Master | 1 | 60

## Guidelines
Priority | Description
Must | Will be included in MVP
Should | Could be in the next phase
Could | Features which enhanceming the product
Would | Nice To Have
Risk | Description
No Risk (1) | The task is standard, previously done before, fully understood, and with stable requirements. No integrations, no dependencies, and no expected surprises. Fully predictable execution.
Low (1.1) | Minor uncertainty exists. The task includes slight variations from previous work, small UI/UX changes, or simple API interactions. Requirements are mostly clear with minimal change expected. Low dependency on other teams.
Medium (1.25) | Moderate complexity or uncertainty. The task involves new data mapping, multi-step workflow, or integration with partially documented services. Requirements may need clarification. There are dependencies with multiple stakeholders or teams.
High (1.5) | High complexity or uncertainty. The task involves new technology, advanced integrations, multi-module impact, compliance/security constraints, or unclear/volatile requirements. High probability of changes, unknowns, or delays.
Size | Description
0 (0) | excluded or already exist
XS (2)
S (5)
M (10)
L (17)
XL (32)