## Features
Module | Feature | Criteria | Estimate | Risk | Total Time | Priority | Notes
Driver App (Flutter) | Approval Pending / Rejected UX | Show onboarding status (pending/approved/rejected) with guidance and next steps. | XS (2) | No Risk (1) | 2 | Must
Driver App (Flutter) | Background Location Sharing (Driver) | Foreground service (Android) + background modes (iOS) to continuously share driver location during online/active trip; battery-safe throttling; permission flows. | S (5) | Medium (1.25) | 6.25 | Must | requires careful platform configuration.
Driver App (Flutter) | Driver Cancellation | Cancel ride with mandatory reason, confirmation dialogs, penalty warnings (if any). | XS (2) | No Risk (1) | 2 | Must
Driver App (Flutter) | Driver Document Upload | Upload required documents (ID, licenses, etc.), image/PDF support, progress, resubmission flows. | XS (2) | No Risk (1) | 2 | Must | Depends on required doc list; integrates camera/gallery.
Driver App (Flutter) | Driver Home + Availability Toggle | Online/offline switch, status banner, current ride indicator, map baseline. | S (5) | No Risk (1) | 5 | Must
Driver App (Flutter) | Driver Onboarding Forms (Profile) | Capture driver personal details & required fields; validation; status screens. | XS (2) | No Risk (1) | 2 | Must
Driver App (Flutter) | Driver Trip History | List completed trips, trip details, filters basic. | XS (2) | No Risk (1) | 2 | Must
Driver App (Flutter) | Earnings Summary | Trip-level earnings list and summary totals (no payouts). | S (5) | No Risk (1) | 5 | Must
Driver App (Flutter) | Incoming Ride Request | Ride request card, accept/decline, timeout UX, sound/vibration, lockscreen behavior (best effort). | S (5) | No Risk (1) | 5 | Must | Depends on push payload and foreground/background handling.
Driver App (Flutter) | Navigate to Pickup / Destination (Driver) | Launch external navigation (Google Maps) with coordinates; fallback if not installed. | XS (2) | Low (1.1) | 2.2 | Must | Avoids building turn-by-turn navigation in-app.
Driver App (Flutter) | Notification Handling (Driver) | Handle push navigation to incoming requests/trip screens; foreground banners; sound policy. | S (5) | Low (1.1) | 5.5 | Must
Driver App (Flutter) | Registration & Login | Driver login/signup using OTP, resend/expiry UX, logout. | XS (2) | No Risk (1) | 2 | Must | reuse shared auth components.
Driver App (Flutter) | SOS | SOS button UX during active trip, confirmation, status feedback. | XS (2) | No Risk (1) | 2 | Must
Driver App (Flutter) | Trip Execution | Screens for arrived/start trip/end trip; safety access; handling network drop/retry. | S (5) | Medium (1.25) | 6.25 | Must
Rider App (Flutter) | Cancel Ride | Cancel confirmation, reason list, fee warning display (if any), success/error handling. | S (5) | No Risk (1) | 5 | Must
Rider App (Flutter) | Destination Search & Selection | Search places, show suggestions, select destination, recent places (optional). | XS (2) | Low (1.1) | 2.2 | Must | Depends on Maps provider APIs exposed by backend or direct SDK.
Rider App (Flutter) | Fare Estimate & Trip Summary Preview | Display estimated fare, distance, duration/ETA; confirmation. | S (5) | No Risk (1) | 5 | Must
Rider App (Flutter) | Home Map + Pickup Location Selection | Map view centered on user, pickup pin selection, current location button, permission prompts. | XS (2) | No Risk (1) | 2 | Must | Google Maps Flutter plugin; handles GPS permission and errors.
Rider App (Flutter) | Live Trip Tracking Map | Show driver on map, route polyline (optional), dynamic ETA, follow mode, map performance. | XS (2) | No Risk (1) | 2 | Must | Real-time updates via sockets/stream/polling.
Rider App (Flutter) | Notification Handling (Rider) | Handle push notification navigation to ride screens; in-app banners; badge counters (optional). | XS (2) | No Risk (1) | 2 | Must
Rider App (Flutter) | Payment UI Flow | Payment initiation mobile; redirect/WebView/SDK handling; success/failure screens; retry UX. | S (5) | Medium (1.25) | 6.25 | Must | Depends on PSP integration method (web redirect vs SDK).
Rider App (Flutter) | Rate Trip | Rating input, feedback form, submit success/failure UX. | XS (2) | No Risk (1) | 2 | Must
Rider App (Flutter) | Registration & Login | Mobile number entry, OTP input, resend/expiry UX, error states, logout flow. | XS (2) | No Risk (1) | 2 | Must
Rider App (Flutter) | Ride Request Flow | Request ride confirmation, searching state, assigned driver details, countdown/timeout UX. | S (5) | Low (1.1) | 5.5 | Must
Rider App (Flutter) | Ride Status Screen (Lifecycle UI) | states for assigned/arrived/started/completed/cancelled; handle reconnect and refresh. | XS (2) | No Risk (1) | 2 | Must
Rider App (Flutter) | Rider Identity Verification | Capture National ID (front/back) + selfie, image quality guidance, upload progress, status (pending/approved/rejected). | XS (2) | No Risk (1) | 2 | Must | Uses camera + image picker; depends on provider UX requirements.
Rider App (Flutter) | Rider Profile (View/Edit) | Profile view & edit screens; validation; language preference; account status. | XS (2) | No Risk (1) | 2 | Must
Rider App (Flutter) | SOS | SOS button UX during active trip, confirmation, status feedback; quick access design. | XS (2) | No Risk (1) | 2 | Must | Backend handles escalation; mobile handles UX and event send.
Rider App (Flutter) | Trip Completion & Receipt | Trip summary screen, fare breakdown, payment status, driver info, next actions. | XS (2) | No Risk (1) | 2 | Must
Rider App (Flutter) | Trip History | List past trips, filter basics, trip details screen. | XS (2) | No Risk (1) | 2 | Must
Rider App (Flutter) | Trip Sharing | Share trip link/details to contacts via OS share sheet; copy link; optional SMS share. | XS (2) | No Risk (1) | 2 | Should
Mobile / Shared | Client Logging & Crash Reporting | In-app logs, crash reporting integration, basic breadcrumbs for debugging (no BI). | S (5) | No Risk (1) | 5 | Should | e.g: Firebase Crashlytics / Sentry.
Mobile / Shared | Localization (AR/EN) + RTL Support | Internationalization, Arabic RTL layout validation, language switch, date/number formats. | S (5) | No Risk (1) | 5 | Must | Assumes translations provided.
Mobile / Shared | Permissions Framework & setup | Unified permission handling for location, camera, storage/photos, notifications; user education screens;deeplink;..etc;Secure Storage & Session Handling | S (5) | No Risk (1) | 5 | Must
Mobile / Shared | Push Notifications Setup (FCM/APNs) | Integrate Firebase Cloud Messaging for iOS/Android, handle token registration, background/foreground handling. | XS (2) | No Risk (1) | 2 | Must | Includes payload parsing + deep-link routing.
Mobile / Shared | Trip Chat | Reusable chat component: message list, input, send state, timestamps, basic moderation messages; trip-scoped. | M (10) | Medium (1.25) | 12.5 | Must | Backend provides token/channel; no media/voice in MVP.

## Estimate Summary
Team Efforts
Development Effort | 126.65 | Days
Number of Dev members | 2 | Developers
Release planning | 0.5 | #
Sprint Zero | 1 | #
Stabilization Sprints | 1 | #
Fixing Security Risks | 0.5 | #
Deployment | 0.5 | #
Expected sprints | 9.8325 | Sprints | 10 working days per sprint
Project Resources
Role | Count | Duration (days) | Notes
Mobile app Team Leader | 1 | 98
Mobile app Senior Developer | 1 | 98
Senior QC engineer | 1 | 50
UIUX designer | 1 | 35
Product Owner | 1 | 50
Scrum Master | 1 | 50

## Guidelines
Priority | Description
Must | Will be included in MVP
Should | Could be in the next phase
Could | Features which enhanceming the product
Would | Nice To Have
Risk | Description
No Risk (1) | The task is standard, previously done before, fully understood, and with stable requirements. No integrations, no dependencies, and no expected surprises. Fully predictable execution.
Low (1.1) | Minor uncertainty exists. The task includes slight variations from previous work, small UI/UX changes, or simple API interactions. Requirements are mostly clear with minimal change expected. Low dependency on other teams.
Medium (1.25) | Moderate complexity or uncertainty. The task involves new data mapping, multi-step workflow, or integration with partially documented services. Requirements may need clarification. There are dependencies with multiple stakeholders or teams.
High (1.5) | High complexity or uncertainty. The task involves new technology, advanced integrations, multi-module impact, compliance/security constraints, or unclear/volatile requirements. High probability of changes, unknowns, or delays.
Size | Description
0 (0) | excluded or already exist
XS (2)
S (5)
M (10)
L (17)
XL (32)