## Features
Module | Feature | Criteria | Estimate | Risk | Total Time | Priority | Notes | Team Ownership
7.1 Rider App | Registration with mobile OTP | The system shall allow Riders to register using an Egyptian mobile number, verified via a one-time SMS password. | XS (2) | High (1.5) | 3 | Must |  | Mix
7.1 Rider App | Login, logout & session management | The system shall provide Riders with secure login, logout, and persistent session management with defined session expiry. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.1 Rider App | Profile management | The system shall allow Riders to view and edit their name, profile photo, email, and language preference. | XS (2) | High (1.5) | 3 | Must |  | Mix
7.1 Rider App | Emergency contacts management | The system shall allow Riders to add, edit, and remove up to three trusted contacts and SOS notifications. | S (5) | Medium (1.25) | 6.25 | Must |  | Mix
7.1 Rider App | Map-based home screen - Pickup location selection - Destination selection | The system shall present Riders with a map-based home screen showing current location, recent destinations, and a primary call-to-action to request a ride. | M (10) | Medium (1.25) | 12.5 | Must |  | Mix (Mobile first)
7.1 Rider App |  | The system shall allow Riders to set the pickup location via GPS auto-detection, manual map pin placement, or selection from saved places. | [5 empty] | Mix
7.1 Rider App |  | The system shall allow Riders to set the destination by searching by name or address, placing a manual map pin, or selecting from saved places. | [5 empty] | Mix
7.1 Rider App | Fare estimate before booking | The system shall display an estimated fare and trip duration to the Rider before request submission, calculated using configured zone-based pricing rules. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Payment method selection | The system shall allow Riders to select between cash and digital (saved or new card) as the payment method for each ride. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Submit ride request | The system shall allow Riders to submit a ride request after confirming pickup, destination, payment method, and child accompaniment information. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Driver matching status & wait screen | The system shall display a 'searching for driver' status to Riders during driver matching, with the option to cancel before driver assignment. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Driver info card | The system shall display the assigned Driver's photo, name, vehicle make/model/colour, plate number, and average rating to the Rider upon assignment. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Real-time driver tracking on map | The system shall provide Riders with real-time map tracking of the assigned Driver, with continuously updated estimated time of arrival. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.1 Rider App | Trip status timeline | The system shall present Riders with a visual timeline showing trip progress through the states: assigned, driver arrived, trip started, and trip completed. | XS (2) | Medium (1.25) | 2.5 | Must |  | Mix
7.1 Rider App | In-app text chat with driver | The system shall provide Riders with limited in-app text messaging to the assigned Driver during the active ride, with messaging disabled after trip completion. | S (5) | Low (1.1) | 5.5 | Must |  | Mix
7.1 Rider App | Cancel ride with reason | The system shall allow Riders to cancel a ride before trip starting, requiring selection of a reason from a predefined list, and shall display any applicable cancellation fee before confirmation. | XS (2) | Medium (1.25) | 2.5 | Must |  | Mix
7.1 Rider App | Trip completion & fare breakdown | The system shall display the final fare with itemised breakdown (base, distance, time, fees) to the Rider upon trip completion. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.1 Rider App | Cash payment confirmation flow | The system shall require both Rider and Driver confirmation of cash payment for cash trips, closing the trip only upon dual confirmation. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Digital payment processing flow | The system shall capture authorised digital payment from the Rider's selected card upon trip completion and display the payment outcome to the Rider. | S (5) | High (1.5) | 7.5 | Must |  | Mix
7.1 Rider App | Rate driver + feedback | The system shall allow Riders to rate the Driver on a 1-to-5 scale and submit categorical tags and free-text feedback after trip completion. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Trip history & receipts | The system shall provide Riders with a chronological list of past trips, including date, route, fare, payment method, and access to trip receipts. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.1 Rider App | Saved places | The system shall allow Riders to save home, work, and custom locations for quick selection during booking. | XS (2) | High (1.5) | 3 | Must |  | Mix
7.1 Rider App | Language switcher (AR/EN, RTL) | The system shall allow Riders to switch the application language between Arabic (with full right-to-left support) and English, with the selection persisting across sessions. | XS (2) | No Risk (1) | 2 | Must |  | Mobile only
7.1 Rider App | Help & support contact | The system shall provide Riders with access to in-app FAQs, a contact form, and direct contact channels to customer support. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.2 Driver App | Registration with mobile OTP | The system shall allow Drivers to register using an Egyptian mobile number, verified via a one-time SMS password. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Login & session management | The system shall provide Drivers with secure login, logout, and persistent session management with defined session expiry. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.2 Driver App | Profile management | The system shall allow Drivers to view and edit their name, profile photo, contact information, and language preference. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.2 Driver App | Identity verification (ID upload) | The system shall require Drivers to upload national ID (front and back) as part of onboarding. Verification is performed manually by Operations via the Admin Portal (no automated OCR or face-match in MVP). | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Driving license upload | The system shall require Drivers to upload front and back images of a valid Egyptian driving license as part of onboarding; validation of format, expiry, and category is performed manually by Operations. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Vehicle documents upload | The system shall require Drivers to upload current vehicle registration and valid insurance documents as part of onboarding. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Vehicle photo upload | The system shall require Drivers to upload exterior photographs of their vehicle so that Riders can visually identify the assigned vehicle. | S (5) | Low (1.1) | 5.5 | Must |  | Mix
7.2 Driver App | Background check consent flow | The system shall require Drivers to acknowledge and consent to a background check before document review proceeds. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Onboarding status tracking | The system shall display the current onboarding status to Drivers across each stage (documents submitted, under review, approved, or rejected). | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Online / offline toggle | The system shall provide Drivers with a single-tap toggle to switch between online (available) and offline (unavailable) status. | S (5) | Medium (1.25) | 6.25 | Must |  | Mix
7.2 Driver App | Incoming request popup with timer (10s) | The system shall present incoming ride requests to available Drivers as a popup containing rider, route, and fare information, automatically dismissing after a defined timeout. | S (5) | Medium (1.25) | 6.25 | Must |  | Mix
7.2 Driver App | Accept / decline ride request | The system shall allow Drivers to accept or decline incoming ride requests within the timeout window, triggering reassignment upon decline or timeout. | S (5) | Medium (1.25) | 6.25 | Must |  | Mix
7.2 Driver App | Pickup navigation | The system shall provide Drivers with a deep link to a default mapping application for turn-by-turn navigation to the Rider's pickup location. | S (5) | Medium (1.25) | 6.25 | Must |  | Mobile only
7.2 Driver App | Arrived at pickup confirmation | The system shall allow Drivers to confirm arrival at the pickup location, triggering rider notification and starting the pickup wait window. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Start trip | The system shall allow Drivers to start the trip after pickup, transitioning the trip lifecycle to 'in progress' and initiating real-time location streaming. | S (5) | High (1.5) | 7.5 | Must |  | Mix
7.2 Driver App | In-trip navigation | The system shall provide Drivers with a deep link to a default mapping application for navigation to the destination during an active trip. | S (5) | No Risk (1) | 5 | Must |  | Mobile only
7.2 Driver App | Complete trip | The system shall allow Drivers to complete the trip upon reaching the destination, triggering fare calculation and payment processing. | S (5) | Low (1.1) | 5.5 | Must |  | Mix
7.2 Driver App | Cancel ride with reason | The system shall allow Drivers to cancel an assigned ride before trip completion, requiring a reason from a predefined list, with repeated cancellations flagged for review. | S (5) | Low (1.1) | 5.5 | Must |  | Mix
7.2 Driver App | Cash collection confirmation | The system shall allow Drivers to confirm cash payment receipt for cash trips, matched against the Rider's confirmation to close the trip. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Trip history list | The system shall provide Drivers with a chronological list of completed trips, including route, fare, and rider rating. | S (5) | Low (1.1) | 5.5 | Must |  | Mix
7.2 Driver App | Earnings dashboard | The system shall provide Drivers with a daily, weekly, and per-trip earnings dashboard, including platform commission breakdown. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.2 Driver App | Rate rider + feedback | The system shall allow Drivers to rate the Rider on a 1-to-5 scale and submit categorical tags after trip completion. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | SOS button (in-trip) | The system shall provide Drivers with an SOS button accessible during an active trip that triggers the safety alert workflow. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | In-app chat with rider | The system shall provide Drivers with limited in-app text messaging to the assigned Rider during the active ride, with messaging disabled after trip completion. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.2 Driver App | Help & support contact | The system shall provide Drivers with access to in-app FAQs, a support form, and direct contact channels to customer support. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.2 Driver App | Language switcher (AR/EN) | The system shall allow Drivers to switch the application language between Arabic and English, with the selection persisting across sessions. | S (5) | No Risk (1) | 5 | Must |  | Mobile only
7.2 Driver App | Rider gender confirmation on first ride (NEW) | On a Rider's first completed trip, the system shall prompt the assigned Driver to confirm that the Rider is female. The confirmation result shall mark the Rider as verified (or flag the account for Operations review) and shall be recorded against the Rider account for audit. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.5 Payments (Cash + Digital) | Card tokenization & saved cards | The system shall securely tokenise Rider card details via the PSP and allow Riders to save cards for use in future trips. | XS (2) | High (1.5) | 3 | Must |  | Mobile only
7.5 Payments (Cash + Digital) | Payment authorization on trip start | The system shall pre-authorise the estimated fare amount on the Rider's payment method when the trip starts. | XS (2) | High (1.5) | 3 | Must |  | Mobile only
7.5 Payments (Cash + Digital) | Payment capture on trip completion | The system shall capture the final fare amount after trip completion, supporting partial-capture scenarios. | XS (2) | High (1.5) | 3 | Must |  | Mobile only
7.5 Payments (Cash + Digital) | Driver cash balance ledger | The system shall maintain a per-Driver ledger of cash trips, commission accrued, and amounts owed to the platform. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Driver-rider matching algorithm | The system shall match each ride request to the most suitable eligible Driver based on proximity, working zone, and driver rating. |  |  | 6.25 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Ride request broadcasting | The system shall broadcast ride requests to candidate Drivers, sequentially, within a defined timeout window (10 seconds). |  |  | 7.5 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Driver acceptance handling | The system shall process Driver acceptance with an atomic lock to prevent multiple Drivers from being assigned to the same ride. |  |  | 2 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Decline / timeout reassignment logic | The system shall re-broadcast a ride request to the next eligible Driver upon decline or response timeout. |  |  | 6.25 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Trip lifecycle state machine | The system shall enforce valid state transitions across the trip lifecycle: requested, assigned, arrived, started, completed, and cancelled. |  |  | 2 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Real-time location streaming | The system shall stream the Driver's location during an active trip to the Rider App and the Operations portal. | S (5) | High (1.5) | 7.5 | Must |  | Mix
7.8 Safety & SOS | Live trip sharing (rider) | The system shall provide a shareable live link to a Rider's trip status, automatically delivered to Trusted Contacts on trip start or SOS activation. | S (5) | High (1.5) | 7.5 | Must |  | Mix
7.9 Notifications | Push notification service (FCM / APNS) | The system shall integrate with Firebase Cloud Messaging (Android) and Apple Push Notification Service (iOS) for push delivery, with managed device-token storage. | S (5) | Low (1.1) | 5.5 | Must |  | Mix
7.9 Notifications | In-app notification center | The system shall provide a persistent in-app inbox of recent notifications in the Rider, Driver, and Administrator applications. | XS (2) | No Risk (1) | 2 | Must |  | Mix

## Estimate Summary
Team Efforts
Development Effort | 258.75 | Days
Number of Dev members | 5 | Developers
Release planning | 0.5 | #
Sprint Zero | 1 | #
Stabilization Sprints | 1 | #
Fixing Security Risks | 0.5 | #
Deployment | 0.5 | #
Expected sprints | 8.675 | Sprints | 10 working days per sprint
Project Resources
Role | Count | Duration (days) | Notes
Fullstack Team Lead | 1 | 95
Fullstack Senior Developer | 3 | 95
Fullstack Junior Developer | 1 | 95
Senior QC engineer | 1 | 95
UIUX designer | 1 | 35
UI developer | 0 | 0
Product Owner | 1 | 95
Scrum Master | 1 | 60

## Guidelines
Priority | Description
Must | Will be included in MVP
Should | Could be in the next phase
Could | Features which enhanceming the product
Would | Nice To Have
Risk | Description
No Risk (1) | The task is standard, previously done before, fully understood, and with stable requirements. No integrations, no dependencies, and no expected surprises. Fully predictable execution.
Low (1.1) | Minor uncertainty exists. The task includes slight variations from previous work, small UI/UX changes, or simple API interactions. Requirements are mostly clear with minimal change expected. Low dependency on other teams.
Medium (1.25) | Moderate complexity or uncertainty. The task involves new data mapping, multi-step workflow, or integration with partially documented services. Requirements may need clarification. There are dependencies with multiple stakeholders or teams.
High (1.5) | High complexity or uncertainty. The task involves new technology, advanced integrations, multi-module impact, compliance/security constraints, or unclear/volatile requirements. High probability of changes, unknowns, or delays.
Size | Description
0 (0) | excluded or already exist
XS (2)
S (5)
M (10)
L (17)
XL (32)