## Features
Module | Feature | Criteria | Estimate | Risk | Total Time | Priority | Notes | Team Ownership
7.1 Rider App | Registration with mobile OTP | The system shall allow Riders to register using an Egyptian mobile number, verified via a one-time SMS password. | XS (2) | Low (1.1) | 2.2 | Must |  | Mix
7.1 Rider App | Login, logout & session management | The system shall provide Riders with secure login, logout, and persistent session management with defined session expiry. | XS (2) | Medium (1.25) | 2.5 | Must |  | Mix
7.1 Rider App | Profile management | The system shall allow Riders to view and edit their name, profile photo, email, and language preference. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Emergency contacts management | The system shall allow Riders to add, edit, and remove up to three trusted contacts, and SOS notifications. | S (5) | Medium (1.25) | 6.25 | Must |  | Mix
7.1 Rider App | Map-based home screen - Pickup location selection - Destination selection | The system shall present Riders with a map-based home screen showing current location, recent destinations, and a primary call-to-action to request a ride. | M (10) | Medium (1.25) | 12.5 | Must |  | Mix (Mobile first)
7.1 Rider App |  | The system shall allow Riders to set the pickup location via GPS auto-detection, manual map pin placement, or selection from saved places. |  |  |  | Must |  | Mix
7.1 Rider App |  | The system shall allow Riders to set the destination by searching by name or address, placing a manual map pin, or selecting from saved places. |  |  |  | Must |  | Mix
7.1 Rider App | Fare estimate before booking | The system shall display an estimated fare and trip duration to the Rider before request submission, calculated using configured zone-based pricing rules. | XS (2) | Medium (1.25) | 2.5 | Must |  | Mix
7.1 Rider App | Payment method selection | The system shall allow Riders to select between cash and digital (saved or new card) as the payment method for each ride. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Submit ride request | The system shall allow Riders to submit a ride request after confirming pickup, destination, payment method, and child accompaniment information. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Driver matching status & wait screen | The system shall display a 'searching for driver' status to Riders during driver matching, with the option to cancel before driver assignment. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Driver info card | The system shall display the assigned Driver's photo, name, vehicle make/model/colour, plate number, and average rating to the Rider upon assignment. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Real-time driver tracking on map | The system shall provide Riders with real-time map tracking of the assigned Driver, with continuously updated estimated time of arrival. | S (5) | High (1.5) | 7.5 | Must |  | Mix
7.1 Rider App | Trip status timeline | The system shall present Riders with a visual timeline showing trip progress through the states: assigned, driver arrived, trip started, and trip completed. | S (5) | High (1.5) | 7.5 | Must |  | Mix
7.1 Rider App | In-app text chat with driver | The system shall provide Riders with limited in-app text messaging to the assigned Driver during the active ride, with messaging disabled after trip completion. | S (5) | High (1.5) | 7.5 | Must |  | Mix
7.1 Rider App | Cancel ride with reason | The system shall allow Riders to cancel a ride before trip starting, requiring selection of a reason from a predefined list, and shall display any applicable cancellation fee before confirmation. | XS (2) | Low (1.1) | 2.2 | Must |  | Mix
7.1 Rider App | Trip completion & fare breakdown | The system shall display the final fare with itemised breakdown (base, distance, time, fees) to the Rider upon trip completion. | S (5) | Medium (1.25) | 6.25 | Must |  | Mix
7.1 Rider App | Cash payment confirmation flow | The system shall require both Rider and Driver confirmation of cash payment for cash trips, closing the trip only upon dual confirmation. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Digital payment processing flow | The system shall capture authorised digital payment from the Rider's selected card upon trip completion and display the payment outcome to the Rider. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Rate driver + feedback | The system shall allow Riders to rate the Driver on a 1-to-5 scale and submit categorical tags and free-text feedback after trip completion. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Trip history & receipts | The system shall provide Riders with a chronological list of past trips, including date, route, fare, payment method, and access to trip receipts. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Saved places | The system shall allow Riders to save home, work, and custom locations for quick selection during booking. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.1 Rider App | Language switcher (AR/EN, RTL) | The system shall allow Riders to switch the application language between Arabic (with full right-to-left support) and English, with the selection persisting across sessions. | S (5) | No Risk (1) | 5 | Must |  | Mobile only
7.1 Rider App | Help & support contact | The system shall provide Riders with access to in-app FAQs, a contact form, and direct contact channels to customer support. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Registration with mobile OTP | The system shall allow Drivers to register using an Egyptian mobile number, verified via a one-time SMS password. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Login & session management | The system shall provide Drivers with secure login, logout, and persistent session management with defined session expiry. | XS (2) | Medium (1.25) | 2.5 | Must |  | Mix
7.2 Driver App | Profile management | The system shall allow Drivers to view and edit their name, profile photo, contact information, and language preference. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Identity verification (ID upload) | The system shall require Drivers to upload national ID (front and back) as part of onboarding. Verification is performed manually by Operations via the Admin Portal (no automated OCR or face-match in MVP). | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Driving license upload | The system shall require Drivers to upload front and back images of a valid Egyptian driving license as part of onboarding; validation of format, expiry, and category is performed manually by Operations. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Vehicle documents upload | The system shall require Drivers to upload current vehicle registration and valid insurance documents as part of onboarding. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Vehicle photo upload | The system shall require Drivers to upload exterior photographs of their vehicle so that Riders can visually identify the assigned vehicle. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Background check consent flow | The system shall require Drivers to acknowledge and consent to a background check before document review proceeds. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Onboarding status tracking | The system shall display the current onboarding status to Drivers across each stage (documents submitted, under review, approved, or rejected). | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Online / offline toggle | The system shall provide Drivers with a single-tap toggle to switch between online (available) and offline (unavailable) status. | S (5) | Medium (1.25) | 6.25 | Must |  | Mix
7.2 Driver App | Incoming request popup with timer (10s) | The system shall present incoming ride requests to available Drivers as a popup containing rider, route, and fare information, automatically dismissing after a defined timeout. | S (5) | Medium (1.25) | 6.25 | Must |  | Mix
7.2 Driver App | Accept / decline ride request | The system shall allow Drivers to accept or decline incoming ride requests within the timeout window, triggering reassignment upon decline or timeout. | S (5) | Medium (1.25) | 6.25 | Must |  | Mix
7.2 Driver App | Pickup navigation | The system shall provide Drivers with a deep link to a default mapping application for turn-by-turn navigation to the Rider's pickup location. | 0 (0) | No Risk (1) | 0 | Must |  | Mobile only
7.2 Driver App | Arrived at pickup confirmation | The system shall allow Drivers to confirm arrival at the pickup location, triggering rider notification and starting the pickup wait window. | S (5) | High (1.5) | 7.5 | Must |  | Mix
7.2 Driver App | Start trip | The system shall allow Drivers to start the trip after pickup, transitioning the trip lifecycle to 'in progress' and initiating real-time location streaming. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | In-trip navigation | The system shall provide Drivers with a deep link to a default mapping application for navigation to the destination during an active trip. | 0 (0) | No Risk (1) | 0 | Must |  | Mobile only
7.2 Driver App | Complete trip | The system shall allow Drivers to complete the trip upon reaching the destination, triggering fare calculation and payment processing. | S (5) | Medium (1.25) | 6.25 | Must |  | Mix
7.2 Driver App | Cancel ride with reason | The system shall allow Drivers to cancel an assigned ride before trip completion, requiring a reason from a predefined list, with repeated cancellations flagged for review. | S (5) | Low (1.1) | 5.5 | Must |  | Mix
7.2 Driver App | Cash collection confirmation | The system shall allow Drivers to confirm cash payment receipt for cash trips, matched against the Rider's confirmation to close the trip. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Trip history list | The system shall provide Drivers with a chronological list of completed trips, including route, fare, and rider rating. | XS (2) | High (1.5) | 3 | Must |  | Mix
7.2 Driver App | Earnings dashboard | The system shall provide Drivers with a daily, weekly, and per-trip earnings dashboard, including platform commission breakdown. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | Rate rider + feedback | The system shall allow Drivers to rate the Rider on a 1-to-5 scale and submit categorical tags after trip completion. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | SOS button (in-trip) | The system shall provide Drivers with an SOS button accessible during an active trip that triggers the safety alert workflow. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.2 Driver App | In-app chat with rider | The system shall provide Drivers with limited in-app text messaging to the assigned Rider during the active ride, with messaging disabled after trip completion. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.2 Driver App | Help & support contact | The system shall provide Drivers with access to in-app FAQs, a support form, and direct contact channels to customer support. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.2 Driver App | Language switcher (AR/EN) | The system shall allow Drivers to switch the application language between Arabic and English, with the selection persisting across sessions. | S (5) | No Risk (1) | 5 | Must |  | Mobile only
7.2 Driver App | Rider gender confirmation on first ride (NEW) | On a Rider's first completed trip, the system shall prompt the assigned Driver to confirm that the Rider is female. The confirmation result shall mark the Rider as verified (or flag the account for Operations review) and shall be recorded against the Rider account for audit. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.3 Admin & Operations Portal | Admin authentication with 2FA | The system shall require Administrators to authenticate using credentials and a second factor (TOTP or SMS), with enforced session timeout. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Role-based access control | The system shall enforce role-based access control across portal features and data, supporting roles including Administrator, Operations Supervisor, Customer Support, Finance, and Compliance. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Live operational dashboard | The system shall provide Administrators with a live dashboard displaying key operational indicators, including active rides, online drivers, open SOS events, and payment failures. | L (17) | High (1.5) | 25.5 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Driver onboarding queue | The system shall present Administrators with a queue of Drivers awaiting review, with filtering by status and submission date. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Driver document review (manual verification) | The system shall allow Administrators to inspect submitted Driver identity, license, and vehicle documents and to approve or reject onboarding with a captured reason. Verification is fully manual (no automated OCR/face-match) for MVP. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Driver account management | The system shall allow Administrators to activate, suspend, or deactivate Driver accounts, with each action recorded in the audit trail. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Rider account management | The system shall allow Administrators to search, view, suspend, or block Rider accounts, including viewing trip history and rider-verification status (from first-ride driver confirmation). | M (10) | No Risk (1) | 10 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Active rides list with filters | The system shall provide Administrators with a tabular view of active rides, with filters for zone, status, payment method, and child accompaniment. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Ride detail view | The system shall provide Administrators with a complete trip-detail view, including event timeline, location trail, payment, and communication log. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Cancellation review queue | The system shall provide Administrators with a list of recent cancellations and their reasons. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Incident management workflow | The system shall allow Administrators to log incidents linked to specific rides or users, assign owners, track resolution, and close incidents with notes. | M (10) | High (1.5) | 15 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Neighborhood / zone management | The system shall allow Administrators to define neighborhood polygons on a map and to activate, deactivate, or edit zone boundaries. | S (5) | Medium (1.25) | 6.25 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Pricing configuration per zone | The system shall allow Administrators to configure base fare, per-kilometre and per-minute rates, minimum fare, and zone-pair pricing rules per zone. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Cancellation rule configuration | The system shall allow Administrators to configure cancellation time windows and applicable fees, globally or per zone. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Commission rate configuration | The system shall allow Administrators to configure platform commission percentages globally or per zone. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Cash reconciliation dashboard | The system shall provide Administrators with an aggregate view of cash owed by Drivers versus cash settled, including identification of overdue settlements. | S (5) | Medium (1.25) | 6.25 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Driver cash balance tracking | The system shall provide a per-Driver ledger of cash trips, commission accrued, and settlement history. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Audit logs viewer | The system shall provide a searchable log of all administrative actions, including approvals, suspensions, configuration changes, and refunds. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.3 Admin & Operations Portal | Static content management | The system shall allow Administrators to manage Terms & Conditions, privacy policy, and FAQ content shown in the apps without code deployment. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.3.1 System Parameters Management | Operating hours configuration | The system shall allow authorised Administrators to configure the platform's daily operating window (start time and end time, in local Egyptian time), with changes applying prospectively and recorded in the audit log. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.5 Payments (Cash + Digital) | Driver cash balance ledger | The system shall maintain a per-Driver ledger of cash trips, commission accrued, and amounts owed to the platform. | S (5) | Medium (1.25) | 6.25 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Driver-rider matching algorithm | The system shall match each ride request to the most suitable eligible Driver based on proximity, working zone, and driver rating. | S (5) | Medium (1.25) | 6.25 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Ride request broadcasting | The system shall broadcast ride requests to candidate Drivers, sequentially, within a defined timeout window (10 seconds). | S (5) | High (1.5) | 7.5 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Driver acceptance handling | The system shall process Driver acceptance with an atomic lock to prevent multiple Drivers from being assigned to the same ride. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Decline / timeout reassignment logic | The system shall re-broadcast a ride request to the next eligible Driver upon decline or response timeout. | S (5) | Medium (1.25) | 6.25 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Trip lifecycle state machine | The system shall enforce valid state transitions across the trip lifecycle: requested, assigned, arrived, started, completed, and cancelled. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | Real-time location streaming | The system shall stream the Driver's location during an active trip to the Rider App and the Operations portal. | M (10) | High (1.5) | 15 | Must |  | Mix
7.6 Trip & Dispatch Engine | Geofence detection (pickup & drop-off) | The system shall detect Driver entry into pickup and drop-off zones and trigger relevant lifecycle events. | S (5) | High (1.5) | 7.5 | Must |  | Web/Backend only
7.6 Trip & Dispatch Engine | No-driver-available retry queue | The system shall queue ride requests for re-broadcast with exponential backoff when no eligible Driver is available, notifying the Rider after a defined number of attempts. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.7 Pricing & Neighborhood Zones | Polygon-based neighborhood definition | The system shall allow Administrators to define neighborhood boundaries as map polygons, persisted as geo-fences. | M (10) | High (1.5) | 15 | Must |  | Web/Backend only
7.7 Pricing & Neighborhood Zones | Per-zone base fare configuration | The system shall allow Administrators to set a base fare per zone, applied to trips originating in that zone. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.7 Pricing & Neighborhood Zones | Per-km & per-minute rate configuration ( Rule Pricing Engine ) | The system shall allow Administrators to set distance-based and duration-based rates per zone. | M (10) | Medium (1.25) | 12.5 | Must |  | Web/Backend only
7.7 Pricing & Neighborhood Zones | Minimum fare per zone | The system shall allow Administrators to define a minimum fare per zone to ensure short trips remain commercially viable. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.7 Pricing & Neighborhood Zones | Cancellation fee rules per zone | The system shall allow Administrators to configure cancellation timing windows and fee amounts per zone. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.7 Pricing & Neighborhood Zones | Pricing rule versioning & history | The system shall maintain a history of pricing rule changes with effective dates for audit . | S (5) | Low (1.1) | 5.5 | Must |  | Web/Backend only
7.7 Pricing & Neighborhood Zones | Peak-hour multiplier (Surge) | The system shall optionally apply a configured multiplier to base pricing during defined peak hours per zone. | S (5) | Medium (1.25) | 6.25 | Must |  | Web/Backend only
7.8 Safety & SOS | Live trip sharing (rider) | The system shall provide a shareable live link to a Rider's trip status, automatically delivered to Trusted Contacts on trip start or SOS activation. | S (5) | High (1.5) | 7.5 | Must |  | Mix
7.9 Notifications | SMS gateway integration | The system shall integrate with the configured SMS gateway for delivery of one-time passwords and critical alerts. | XS (2) | Medium (1.25) | 2.5 | Must |  | Web/Backend only
7.9 Notifications | Push notification service (FCM / APNS) | The system shall integrate with Firebase Cloud Messaging (Android) and Apple Push Notification Service (iOS) for push delivery, with managed device-token storage. | S (5) | No Risk (1) | 5 | Must |  | Mix
7.9 Notifications | In-app notification center | The system shall provide a persistent in-app inbox of recent notifications in the Rider, Driver, and Administrator applications. | XS (2) | No Risk (1) | 2 | Must |  | Mix
7.9 Notifications | Email notifications (admin / finance) | The system shall support email delivery for administrative and finance notifications, including reconciliation summaries. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.10 Reporting & Analytics | Daily / weekly ride summary | The system shall produce daily and weekly summary reports of trips, gross merchandise value, completion rate, and average fare, grouped by day, week, and zone. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.10 Reporting & Analytics | Driver performance report | The system shall produce per-Driver performance reports including trips completed, earnings, cancellation rate, average rating, and hours online. | XS (2) | No Risk (1) | 2 | Must |  | Web/Backend only
7.10 Reporting & Analytics | Cancellation analytics report | The system shall produce reports on cancellation reasons, timing patterns, and correlation with zones, Drivers, and Riders. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.10 Reporting & Analytics | Payment reconciliation report | The system shall produce a payment reconciliation report covering cash and digital splits, success and failure rates, and outstanding cash balances. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.10 Reporting & Analytics | Safety incident report | The system shall produce safety incident reports including SOS counts, response times, escalation outcomes, and accounts with repeat incidents. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.10 Reporting & Analytics | Zone performance report | The system shall produce per-zone performance reports including trips, gross merchandise value, supply versus demand balance, and cancellation rate. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.10 Reporting & Analytics | Management KPI dashboard | The system shall provide an executive-level KPI dashboard covering gross merchandise value, active users, retention, safety, and financial health. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only
7.10 Reporting & Analytics | CSV / Excel export | The system shall support exporting filtered data from any report to CSV or Microsoft Excel formats. | S (5) | No Risk (1) | 5 | Must |  | Web/Backend only

## Estimate Summary
Team Efforts
Development Effort | 437.4 | Days
Number of Dev members | 5 | Developers
Release planning | 0.5 | #
Sprint Zero | 1 | #
Stabilization Sprints | 1 | #
Fixing Security Risks | 0.5 | #
Deployment | 0.5 | #
Expected sprints | 12.248 | Sprints | 10 working days per sprint
Project Resources
Role | Count | Duration (days) | Notes
Fullstack Team Lead | 1 | 95
Fullstack Senior Developer | 3 | 95
Fullstack Junior Developer | 1 | 95
Senior QC engineer | 1 | 95
UIUX designer | 1 | 35
UI developer | 0 | 0
Product Owner | 1 | 95
Scrum Master | 1 | 60

## Guidelines
Priority | Description
Must | Will be included in MVP
Should | Could be in the next phase
Could | Features which enhanceming the product
Would | Nice To Have
Risk | Description
No Risk (1) | The task is standard, previously done before, fully understood, and with stable requirements. No integrations, no dependencies, and no expected surprises. Fully predictable execution.
Low (1.1) | Minor uncertainty exists. The task includes slight variations from previous work, small UI/UX changes, or simple API interactions. Requirements are mostly clear with minimal change expected. Low dependency on other teams.
Medium (1.25) | Moderate complexity or uncertainty. The task involves new data mapping, multi-step workflow, or integration with partially documented services. Requirements may need clarification. There are dependencies with multiple stakeholders or teams.
High (1.5) | High complexity or uncertainty. The task involves new technology, advanced integrations, multi-module impact, compliance/security constraints, or unclear/volatile requirements. High probability of changes, unknowns, or delays.
Size | Description
0 (0) | excluded or already exist
XS (2)
S (5)
M (10)
L (17)
XL (32)